Progress with SAV definition for theme Permafrost:

- Phase I of ROADS process documentation sent for review of the ROADS advisory panel.  Advisory panel reviewed the progress and Phase I outcomes as satisfactory. This document outlines the planned expert panel composition, scope and plans for Phase II of the process of defining Shared Arctic Variables

- Phase II of ROADS process initiated in an in-person workshop of the Expert Panel as part of the Arctic Circle Assembly 2023 in Reykjavik Iceland. Societal benefit analysis (one of the main components of Phase II of the ROADS process) has been further continued in an online workshop on the 16th of May 2024. Phase II documentation is currently being written up (as of 21.5.2024) in collaboration with the expert panel, and is expected to be submitted for review in the end of Q2/2024.

- SAV definition work has been discussed in several different international conferences and the feedback has been taken into considerations of the ongoing work.

- Monthly meetings between the SAV definition team for Task 1.1b across themes. Regular participation in ROADS advisory panel meetings. Commenting on documentation for Phase 1 and Phase 2 documentation by ROADS Advisory panel based on experiences during the definition work.

Priority activities for upcoming period:

- Finish Phase II documentation and proposal of initial Shared Arctic Variables.

- Replace experts and find additional experts from identified gaps in stakeholders currently present in the expert panel.